## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Horseshoe Farm | [6 empty] | Completed | 1
| Team Members: | Allison Macdonald, John Carroll, Amanda Bailey, Cesar Sanchez, Mark Ma | [6 empty] | Discarded | 2
| Date: | 2016-02-16 | Cycle: | Architectural Spike |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | Students should be able to log into a website, see notifications, and navigate to tutoring materials easily. Notifications will include progress via horseshoes. Based on the day, either reading or math materials will be presented. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Gather requirements and generate a prototype.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Log In |  | 1 | 6 | 6 | Unstarted | 0 | 0
2 | View Notifications |  | 1 | 4 | 4 | Unstarted | 0 | 0
3 | Select Reading |  | 1 | 2 | 2 | Unstarted | 0 | 0
4 | Start video chat service |  | 2 | 9 | 0 | Unstarted | 0 | 0
5 | Select Math |  | 1 | 2 | 2 | Unstarted | 0 | 0
6 | View Math Worksheets |  | 2 | 5 | 2 | Unstarted | 0 | 0
7 | Admin functionality |  | 2 | 6 | 1 | Unstarted | 0 | 0
|  |  | Planned Total | 28 | 16 | Actual Total | 0 | 0

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Horseshoe Farm
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Allison Macdonald | N/A | N/A | N/A | N/A | 9 | 0 | 0 | 2.5 | 2.5 | 2 | 2 | 0 | 0 | 4.5 | 4.5
| John Carroll |  |  |  |  | 9 | 0 | 0 | [6 empty] | 0 | 0
| Amanda Bailey | N/A | N/A | N/A | N/A | 9 | 0 | 0 | 2.5 | 2.5 | 0.5 | 0.5 | 0 | 0 | 3 | 3
| Cesar Sanchez |  |  |  |  | 9 | [8 empty] | 0 | 0
| Lanxin (Mark) Ma |  |  |  |  | 9 | [8 empty] | 0 | 0
[5 empty] | Totals | 45 | 0 | 0 | 5 | 5 | 2.5 | 2.5 | 0 | 0 | 7.5 | 7.5
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| We have wrapped things up with Dr. Nadarajah and made contact with Dr. Doresy, James, and Josh. We have gathered requirements for the new project and discussed the general layout of the site. | [6 empty] | Configure a log in page that connects to a database (perhaps MySQL). Connect both reading and math to proper website links. Set up notificiations with some dummy messages. Create some tables which contain user info such as progress, username, math/reading day etc.
| Obstacles encountered since last status report: | [6 empty] | Notes:
| With no contact from sponsor until Friday, we did not have a lot of information to proceed with until the weekend started. | [6 empty] | It is clear that we need to reach out to sponsors in order to get more specific information on standard procedure. We'll have to ask around or be clever about designing a relational database which includes data which can be dynamically modified by admins (ie. reading or math day).
Risks facing the project:
It is in the middle of test weeks. Many members are busy with other classes, jobs, and research.

## Member 1 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Allison
Week Ending: |  | 2016-02-15
Cycle: |  | Architectural Spike
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Met with Dr. Chapman on new project. Looked into pricing for 30-50 students 5x a week.
Date: | 2016-02-09 | Result: | GoDaddy will allow up to 50 users to download at the same time. This meets the needs of the sponsor and will cost $120 annually for the economy package.
Hours Worked: | 0.5 | Problems encountered: | Attempted to compare GoDaddy to DreamHost but couldn't find any traffic information on DreamHost. This service was more expensive anyway.
Day: | Wednesday | Task(s) performed: | Responded to Dr. Nada's inquiry about progress on Herd Management project, Researched how to export from AWS, Met with team to discuss plans for Horseshoe project
Date: | 2016-02-10 | Result: | Dr. Nada would like a copy of the data stored on AWS. We will suggest GoDaddy to the new sponsors. We believe the start up framework is a priority.
Hours Worked: | 1 | Problems encountered: | We do not have the data as there was no way to export from AWS. We cannot progress until we talk to the sponsor.
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-02-11 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Met with Dr. Dorsey, Met with Mr. Hancock, Met with James and Josh, forwarded minutes to Mr. Hancock, discussed options with team, emailed Dr. Nada, further research for prototype
Date: | 2016-02-12 | Result: | We have an idea of which tools to use to start the website and a more solidified vision of what the sponsors want from the project. We have offered Dr. Nada the log in for AWS.
Hours Worked: | 2.25 | Problems encountered: | Meeting with Mr. Hancock would have been more fruitful if we'd met with sponsors first.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-02-13 | Result: | N/A
Hours Worked: | ? | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | N/A
Date: | 2016-02-14 | Result: | N/A
Hours Worked: | ? | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Filled out first two sheets of status report.
Date: | 2016-02-15 | Result: | We have something to turn in now.
Hours Worked: | 0.5 | Problems encountered: | Members have not yet filled out their Timesheets, I will have to contact them.

## Member 2 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Amanda
Week Ending: |  | 2016-02-15
Cycle: |  | SPIKE
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Met with Dr. Chapman to discuss the new project. Looked into webhosting sites
Date: | 2016-02-09 | Result: | Team switched from the Goat Herd Management Project to the Horseshoe Farm Project.
Hours Worked: | 1 | Problems encountered: | Other than GoDaddy, the other webhosting sites had hacking scandels attached to them.
Day: | Wednesday | Task(s) performed: | Meeting with team.
Date: | 2016-02-10 | Result: | Decision was made to suggest Go Daddy for the project, as well as to focus on the startup framework instead of the reading app.
Hours Worked: | 0.25 | Problems encountered: | Missed the meeting, because I was still in class and the meeting ran short and had to be filled in afterward.
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-02-11 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Meeting with Mr. Hancock. Meeting with James and Josh.
Date: | 2016-02-12 | Result: | Gained a better understanding of the requirements for the project, and discussed some tools we might be able to use.
Hours Worked: | 0.75 | Problems encountered: | Did not have much to discuss with Mr. Hancock because of a lack of information on the project first.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-02-13 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | N/A
Date: | 2016-02-14 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Reviewed the progess Allison made on the status report. Worked on my section for the status report.
Date: | 2016-02-15 | Result: | The status report has been proof read and the status report neared completion
Hours Worked: | 1 | Problems encountered: | I forgot about the status report, until notified by Allison.

## Member 3 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Cesar Sanchez
Week Ending: |  | 2016-02-15
Cycle: |  | SPIKE
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Talked to Chapman about new project
Date: | 2016-02-09 | Result: | Got assigned new project: Horseshoe Farm
Hours Worked: | 0.75 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Discussed possible layouts/implementations for the tutoring interface/program
Date: | 2016-02-10 | Result: | Have some ideas down and a direction in which we can go
Hours Worked: | 0.25 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-02-11 | Result: | N/A
Hours Worked: | N/A | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | N/A
Date: | 2016-02-12 | Result: | N/A
Hours Worked: | N/A | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-02-13 | Result: | N/A
Hours Worked: | N/A | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | N/A
Date: | 2016-02-14 | Result: | N/A
Hours Worked: | N/A | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Filled in status report
Date: | 2016-02-15 | Result: | My section of status report is filled in
Hours Worked: | 0.25 | Problems encountered: | Need to improve participation

## Member 4 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Lanxin (Mark) Ma
Week Ending: |  | 2016-02-15
Cycle: |  | SPIKE
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2011-12-25 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2011-12-26 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2011-12-27 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2011-12-28 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2011-12-29 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2011-12-30 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2011-12-31 | Result:
Hours Worked: | ? | Problems encountered:

## Member 5 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | John Carroll
Week Ending: |  | 2016-02-15
Cycle: |  | Architectural Spike
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Was assigned a new group project.
Date: | 2016-02-09 | Result: | Acquired broad understanding of the new project's requirements.
Hours Worked: | 1 | Problems encountered: | Sprocket and cog don't fit together correctly. A kotter pin might be required to hold the cog in place.
Day: | Wednesday | Task(s) performed: | Met with Austin regarding status update. We gave him some information regarding what we knew about the new project, and he proceeded to show us technologies that we could implement.
Date: | 2016-02-10 | Result: | Acquired knowledge of technologies.
Hours Worked: | 1 | Problems encountered: | Did not know all of the project's requirments.
Day: | Thursday | Task(s) performed: | Looked into new ways to host a web based client that can fit all of the vaguely known requirements.
Date: | 2016-02-11 | Result: | Godaddy hosting and keeping it solely web-based due to the different platforms.
Hours Worked: | 1 | Problems encountered: | Not yet knowing all of the requirements.
Day: | Friday | Task(s) performed: | Did some correspondence with Dr. Nada regarding the old project's database. Also spoke with the new project horsehoe regarding their requirements.
Date: | 2016-02-12 | Result: | Acquired requirements.
Hours Worked: | 2.25 | Problems encountered: | Location/distance was a be of an issue.
Day: | Saturday | Task(s) performed:
Date: | 2016-02-13 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2016-02-14 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | Write into time sheet
Date: | 2016-02-15 | Result: | Finished writing into time sheet.
Hours Worked: | 1 | Problems encountered: | Was short on time due to work schedule.