## Status Report Page 1
Senior Design Status Report (Page 1) | [9 empty] | List Data - Do Not Edit
| Project Name: | Horseshoe Farm | [7 empty] | Completed | 1
| Team Members: | Allison Macdonald, John Carroll, Amanda Bailey, Cesar Sanchez, Mark Ma | [7 empty] | Discarded | 2
| Date: | 2016-02-22 | Cycle: | Architectural Spike | [5 empty] | Collaboration | 3
Adversarial
| System Metaphor: | Horseshoe Farms has requested a webpage which can help streamline their online tutoring process. Students should be able to log into a website, see notifications, and navigate to tutoring materials easily. Notifications will include progress via horseshoes. Based on the day, either reading or math materials will be presented. | [7 empty] | In Review
Unstarted
| Cycle Intent: | Gather requirements and generate a prototype.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Log In |  | 1 | 9 | 9 | Collaboration | 9 | 9 | Should have anticipated more hours for setting up PHP/MySQL.
2 | View Notifications |  | 1 | 11 |  | Unstarted | 0 | 0
3 | Select Reading |  | 1 | 3 |  | Unstarted | 0 | 0
4 | Start video chat service |  | 2 | 25 |  | Unstarted | 0 | 0
5 | Select Math |  | 1 | 3 |  | Unstarted | 0 | 0
6 | View Math Worksheets |  | 2 | 10 |  | Unstarted | 0 | 0
7 | Admin functionality |  | 2 | 15 |  | Unstarted | 0 | 0
|  |  | Planned Total | 61 | 9 | Actual Total | 9 | 9

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Horseshoe Farm
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Allison Macdonald | 1,2,6,7 | 1 | N/A | N/A | 27 | 0 | 0 | 4 | 6.5 | 1 | 3 | 4 | 4 | 9 | 13.5
| John Carroll | N/A | N/A | N/A | N/A | 27 | 0 | 0 | 2.5 | 2.5 | 2 | 2 | 0 | 0 | 4.5 | 4.5
| Amanda Bailey | N/A | N/A | N/A | N/A | 27 | 0 | 0 | 4.25 | 6.75 | 0.75 | 1.25 | 0 | 0 | 5 | 8
| Cesar Sanchez |  |  |  |  | 27 | 0 | 0 | 3 | 3.5 | 2 | 2 | 0 | 0 | 5 | 5.5
| Lanxin (Mark) Ma | N/A | N/A | N/A | N/A | 27 | 0 | 0 | 2 | 2 | 1.5 | 1.5 | 0 | 0 | 3.5 | 3.5
[5 empty] | Totals | 135 | 0 | 0 | 15.75 | 21.25 | 7.25 | 9.75 | 4 | 4 | 23.5 | 31.5
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Started prototype and selected development tools. | [6 empty] | Have log in fully functional and communicating with database. Have the splash screens for both admin and student up and running. Split user story 7 into several smaller stories.
| Obstacles encountered since last status report: | [6 empty] | Notes:
Scheduling for team meetings was difficult and left us working without a lot of collaboration with one another. We found we didn't have enough specifics from sponsors and had to schedule another meeting with them. Having issues with PHP on localhost.
Risks facing the project:
Not getting PHP working will be a problem.

## Allison's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Allison
Week Ending: |  | 2016-02-22
Cycle: |  | Architectural Spike
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-02-16 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | John will not be able to make it to the meeting tomorrow.
Day: | Wednesday | Task(s) performed: | Research Node.js, PHP, LINQ to SQL, and Jade.js. Set up the HTML framework for a login page. Meeting with team. Database design and set up PHP/MySQL.
Date: | 2016-02-17 | Result: | Will recommend PHP/MySQL to team in meeting today.
Hours Worked: | 6 | Problems encountered: | Having trouble configuring PHP. Phpinfo() script is not functional.
Day: | Thursday | Task(s) performed: | Worked with Amanda and Mark on HTML, CSS, and JS basics.
Date: | 2016-02-18 | Result:
Hours Worked: | 1 | Problems encountered: | I still can't get PHP working.
Day: | Friday | Task(s) performed: | Met with James and Josh. Met with team - began story boarding.
Date: | 2016-02-19 | Result: | We have the begninnings of a story board.
Hours Worked: | 2 | Problems encountered: | I worked my max hours and had to leave town for the weekend.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-02-20 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | N/A
Date: | 2016-02-21 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | N/A
Date: | 2016-02-22 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A

## Amanda's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Amanda
Week Ending: |  | 2016-02-22
Cycle: |  | SPIKE
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-02-16 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | John won't be able to make it to the meeting
Day: | Wednesday | Task(s) performed: | Weekly team meeting and researched if stormpath and node.js would be usefull to the project. Attempted to intall PHP
Date: | 2016-02-17 | Result: | At the meeting it was decided neither would be useful.
Hours Worked: | 1 | Problems encountered: | Neither me or Allison could get PHP installed
Day: | Thursday | Task(s) performed: | Met with Allison to go over the basics of web developement.
Date: | 2016-02-18 | Result: | Now know the basics of web developement
Hours Worked: | 1 | Problems encountered:
Day: | Friday | Task(s) performed: | Met with sponsor for 45 mins and then had a team meeting for an hour.
Date: | 2016-02-19 | Result: | Learned that the sponsor has sketches of what they would like the website to look like and how they want the worksheets to be implemented
Hours Worked: | 1.75 | Problems encountered: | Mark could not show up to the meeting.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-02-20 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | N/A
Date: | 2016-02-21 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Filled out timesheet. Looked into downloading WampServer and XAMPP to solve PHP problem. Researched Web based chat server
Date: | 2016-02-22 | Result: | A completeted time sheet. Learned that skype has a web based version currently in beta.
Hours Worked: | 1.25 | Problems encountered: | WampServer and XAMPP are not yet implemented for Windows 10, so could not download them.

## Cesar's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Cesar Sanchez
Week Ending: |  | 2016-02-22
Cycle: |  | SPIKE
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-02-16 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | John will be unable to attend tomorrow's meeting
Day: | Wednesday | Task(s) performed: | Discussed node.js, PHP, MySQL as well as other options for implementation into the project design
Date: | 2016-02-17 | Result: | PHP will probably be implemented, despite difficulties currently being encountered
Hours Worked: | 1 | Problems encountered: | Had issues getting PHP to properly install
Day: | Thursday | Task(s) performed: | Researched existing pdf libraries for web use
Date: | 2016-02-18 | Result: | Firefox has a built-in library for displaying PDFs that we can use for free. Comes with many useful features
Hours Worked: | 1 | Problems encountered: | I personally don't actually know any web coding
Day: | Friday | Task(s) performed: | Met with sponsors to get more details on project specifics.
Date: | 2016-02-19 | Result: | Know a lot more about requirements and expectations for project. Began storyboarding for project
Hours Worked: | 3 | Problems encountered: | Some requirements appear to be out of reach for this semester
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-02-20 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | N/A
Date: | 2016-02-21 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Filled in status report
Date: | 2016-02-22 | Result: | Status report completed
Hours Worked: | 0.5 | Problems encountered: | None

## Mark's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Lanxin (Mark) Ma
Week Ending: |  | 2016-02-22
Cycle: |  | SPIKE
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-02-16 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | John will not be able to attend the meeting tomorrow.
Day: | Wednesday | Task(s) performed: | Attended weekly team meeting. Researched PHP and SQL. Talked about having an HTML tutorial with Allison.
Date: | 2016-02-17 | Result: | Decided that MySQL and PHP should be used for the team. Planned on meeting with Allison for a HTML tutorial on 2/18/16.
Hours Worked: | 1 | Problems encountered: | Had some issues with PHP.
Day: | Thursday | Task(s) performed: | Met with Allison to go over the basics of HTML web development. Attempted to install notepad++ and symphony on pc.
Date: | 2016-02-18 | Result: | Got the basics of HTML web development and got notepad++ successfully installed on pc.
Hours Worked: | 1.5 | Problems encountered: | Was unable to successfully install symphony on pc.
Day: | Friday | Task(s) performed: | Could not attend the meeting.
Date: | 2016-02-19 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | Was uable to attend the meeting due to some personal out of town business that I had to take care of.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-02-20 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | N/A
Date: | 2016-02-21 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Filled out status report.
Date: | 2016-02-22 | Result: | Status report completed.
Hours Worked: | 1 | Problems encountered: | N/A

## John's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | John Carroll
Week Ending: |  | 2016-02-22
Cycle: |  | Architectural Spike
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Collaborated on user stories and features: notifications, worksheets, screensharing. Also collaborated on technologies to use.
Date: | 2016-02-16 | Result: | Acquired user stories basis, features, and technology ideas.
Hours Worked: | 2 | Problems encountered:
Day: | Wednesday | Task(s) performed: | The group met on discussing which technogies to implement.
Date: | 2016-02-17 | Result: | HTML, CSS, jQuery/JS, and PHP
Hours Worked: | 2 | Problems encountered: | I was absent and following the meeting from afar due to the career fair.
Day: | Thursday | Task(s) performed:
Date: | 2016-02-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed: | Had talkio meeting with sponsors: James and Josh. Discussed with them questions gathered from Wednesday's meeting. Requirements specifics for user stories per account type were gathered. Also, a bit of story boarding page navigations.
Date: | 2016-02-19 | Result: | Acquired the basis in which to begin prototyping using our chosen technologies
Hours Worked: | 3 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2016-02-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Spent time relooking at Friday's user stories for each page
Date: | 2016-02-21 | Result: | Modified the user stories stored on google drive.
Hours Worked: | 1 | Problems encountered: | no group meeting to collaborate on
Day: | Monday | Task(s) performed: | Final check of status report
Date: | 2016-02-22 | Result: | Finalized correctness.
Hours Worked: | 0.5 | Problems encountered: