## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Horseshoe Farm | [6 empty] | Completed | 1
| Team Members: | Allison Macdonald, John Carroll, Amanda Bailey, Cesar Sanchez, Mark Ma | [6 empty] | Discarded | 2
| Date: | 2016-02-29 | Cycle: | Architectural Spike |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | Horseshoe Farms has requested a webpage which can help streamline their online tutoring process. Students should be able to log into a website, see notifications, and navigate to tutoring materials easily. Notifications will include progress via horseshoes. Based on the day, either reading or math materials will be presented. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Gather requirements and generate a prototype.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Student Log In |  | 1 | 25 | 25 | Collaboration |  | 9
2 | Student View Notifications |  | 1 | 15 | 15 | Unstarted | 4 | 0
3 | Student Auto Redirect to Lesson |  | 2 | 10 | 5 | Unstarted |  | 0
4 | Student/Tutor start video chat service |  | 2 | 25 | 5 | Collaboration | 1 | 0
5 | Student view math worksheets |  | 1 | 10 | 10 | Collaboration |  | 0
6 | Student resume reading from last page |  | 3 | 12 | 0 | Unstarted |  | 0
7 | Student preview lesson for the day |  | 3 | 10 | 10 | Collaboration |  | 0
8 | Student/tutor screen share control |  | 3 | 10 | 0 | Unstarted |  | 0
9 | Tutor view daily schedule (student and lesson) |  | 3 | 15 | 0 | Unstarted |  | 0
10 | Secured log in |  | 1 | 10 | 10 | Collaboration | 1 | 0
11 | Admin view student statistics |  | 3 | 20 | 0 | Unstarted |  | 0
12 | Admin view student/tutor pairing history |  | 3 | 15 | 0 | Unstarted
13 | Admin plan student lesson |  | 2 | 25 | 10 | Unstarted |  | 0
|  |  | Planned Total | 202 | 90 | Actual Total | 6 | 9

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Horseshoe Farm
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Allison Macdonald | 1,2,3,7 | 1,2,3,7 | 0 | 0 | 27 | 0 | 0 | 7.5 | 14 | 0 | 3 | 3 | 7 | 10.5 | 24
| John Carroll | 1,2,3,7,10 | 0 | 0 | 0 | 27 | 0 | 0 | 6 | 8.5 | 0 | 2 | 0 | 0 | 6 | 10.5
| Amanda Bailey |  |  |  |  | 27 | 0 | 0 | 4.5 | 11.25 | 0 | 1.25 | 0 | 0 | 4.5 | 12.5
| Cesar Sanchez | 1,2,3,7,10 | 0 | 0 | 0 | 27 | 0 | 0 | 5.25 | 8.75 | 0 | 2 | 0 | 0 | 5.25 | 10.75
| Lanxin (Mark) Ma |  |  |  |  | 27 | 0 | 0 | 4.5 | 8.5 | 0 | 1.5 | 0 | 0 | 4.5 | 10
[5 empty] | Totals | 135 | 0 | 0 | 27.75 | 51 | 0 | 9.75 | 3 | 7 | 26.25 | 57.75
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Set up php with WAMP. Talk with GoDaddy about hosting options and costs. Front-end prototype for student. Specific options determined for worksheets. | [6 empty] | End of cycle, finish up corresponding user stories. Finish Cycle Report.
| Obstacles encountered since last status report: | [6 empty] | Notes:
| Austin out of town - couldn't communicate as frequently. Setting up Apache redirects. Busy school week, people did more senior design work at the tail end of the week. | [6 empty] | I'm tired gg
Risks facing the project:
Cost of database administration. Integration of video. Potential scope creep.

## Allison's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Allison
Week Ending: |  | 2016-02-29
Cycle: |  | Architectural Spike
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-02-23 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Met with team, looked through GoDaddy with the login information provided by sponsors.
Date: | 2016-02-24 | Result: | Generated a few more story boards
Hours Worked: | 2 | Problems encountered: | Found out current site is built on Wordpress. We'll have to see if this is compatible with our project.
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-02-25 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | N/A
Date: | 2016-02-26 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | Fill out status report, communicate with team and sponsors via email. Follow Austin's suggestions concerning PHP. Discuss cost estimates provided by GoDaddy rep, generate user stories, storyboard, front-end prototyping
Date: | 2016-02-27 | Result: | General look for front-end has been hammered out as well as JS redirects. Storyboarding for both student and tutor are finished. User stories are more specific and have more reasonable estimates.
Hours Worked: | 6.33 | Problems encountered: | PHP still not working. Cost of database hosting is certainly a cause for concern.
Day: | Sunday | Task(s) performed: | PHP ON LOCALHOST, Meeting with team
Date: | 2016-02-28 | Result: | IT'S WORKING BOO-YAH!
Hours Worked: | 4.25 | Problems encountered: | Redirecting to a default page - resolved.
Day: | Monday | Task(s) performed: | N/A
Date: | 2016-02-29 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A

## Amanda's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Amanda
Week Ending: |  | 2016-02-29
Cycle: |  | SPIKE
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Tested skype
Date: | 2016-02-23 | Result: | Was able to screen share but did not find out how to take over the other users screen
Hours Worked: | 1 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Team meeting
Date: | 2016-02-24 | Result: | Story boards were created
Hours Worked: | 1 | Problems encountered:
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-02-25 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | N/A
Date: | 2016-02-26 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-02-27 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Team meeting
Date: | 2016-02-28 | Result: | Time sheet worked on. Looked at video sharing options.
Hours Worked: | 2.5 | Problems encountered:
Day: | Monday | Task(s) performed: | N/A
Date: | 2016-02-29 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A

## Cesar's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Cesar Sanchez
Week Ending: |  | 2016-02-29
Cycle: |  | SPIKE
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-02-23 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Team meeting, got password for Godaddy and went through files for the current site.
Date: | 2016-02-24 | Result: | Generated more storyboards for the project
Hours Worked: | 2 | Problems encountered: | Website uses wordpress
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-02-25 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | N/A
Date: | 2016-02-26 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | Austin out of town, did not meet
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-02-27 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Met with team to discuss roles and perform research. Researched how to display PDF files in Chrome.
Date: | 2016-02-28 | Result: | Verified that there are no viable alternatives for granting input control to another computer. Decided that the PDF.js library is our best option with regards to displaying PDF files in a browser
Hours Worked: | 4.25 | Problems encountered: | No alternative for input control
Day: | Monday | Task(s) performed: | Developed storyboards
Date: | 2016-02-29 | Result: | Completed the Admin storyboard
Hours Worked: | 1 | Problems encountered: | None

## Mark's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Lanxin (Mark) Ma
Week Ending: |  | 2016-02-29
Cycle: |  | SPIKE
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-02-23 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Team meeting. Looked though user storyboards.
Date: | 2016-02-24 | Result: | More storyboards were generated.
Hours Worked: | 1.5 | Problems encountered: | Website uses wordpress, so must check to see if site is compatible.
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-02-25 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | N/A
Date: | 2016-02-26 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | Austin was out of town, so did not have meeting.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-02-27 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Met with team. Download PHP file on GitHub desktop app. Tried to get talky.io set up on pc. Started working on PHP code for student login. Fill out status report and timesheet.
Date: | 2016-02-28 | Result: | Got PHP file downloaded on GitHub desktop app. Filled out status report and timesheet.
Hours Worked: | 3 | Problems encountered: | Unable to download talky.io due to lack of camera on pc.
Day: | Monday | Task(s) performed: | N/A
Date: | 2016-02-29 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A

## John's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | John Carroll
Week Ending: |  | 2016-02-29
Cycle: |  | Architectural Spike
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-02-23 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Logged into projecthsf.org's godaddy.com and explored it as a group
Date: | 2016-02-24 | Result: | Created and worded on storyboards
Hours Worked: | 1.5 | Problems encountered: | Website uses wordpress
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-02-25 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Spoke with Godaddy.com sales representative in regards to the sponsor's current hosting capabilities and what it would mean for the application we could possibly implement and host on projecthsf.org's hosting.
Date: | 2016-02-26 | Result: | Acquired options to give to the sponsor.
Hours Worked: | 1.5 | Problems encountered: | None.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-02-27 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Collaborated with group in regards to this week's status report. Worked on next week's objectives, synchronized information, researched and planned implementation of storyboards.
Date: | 2016-02-28 | Result: | Work done!
Hours Worked: | 3 | Problems encountered: | None.
Day: | Monday | Task(s) performed: | N/A
Date: | 2016-02-29 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A