## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Project Horseshoe Farm | [6 empty] | Completed | 1
| Team Members: | Allison Macdonald, John Carroll, Amanda Bailey, Cesar Sanchez, Mark Ma | [6 empty] | Discarded | 2
| Date: | 2016-03-07 | Cycle: | Architectural Spike |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | Horseshoe Farms has requested a webpage which can help streamline their online tutoring process. Students should be able to log into a website, see notifications, and navigate to tutoring materials easily. Notifications will include progress via horseshoes. Based on the day, either reading or math materials will be presented. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Gather requirements and generate a prototype.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Student Log In |  | 1 | 25 | 25 | Collaboration | 9 | 9
2 | Student View Notifications |  | 1 | 15 | 15 | Collaboration | 4 | 4
3 | Student Auto Redirect to Lesson |  | 2 | 10 | 5 | Collaboration |  | 0
4 | Student/Tutor start video chat service |  | 2 | 25 | 5 | Collaboration | 1 | 1
5 | Student view math worksheets |  | 1 | 10 | 10 | Collaboration |  | 0
6 | Student resume reading from last page |  | 3 | 12 | 0 | Unstarted |  | 0
7 | Student preview lesson for the day |  | 3 | 10 | 10 | Collaboration |  | 0
8 | Student/tutor screen share control |  | 3 | 10 | 0 | Unstarted |  | 0
9 | Tutor view daily schedule (student and lesson) |  | 3 | 15 | 0 | Unstarted |  | 0
10 | Secured log in |  | 1 | 10 | 10 | Collaboration | 1 | 1
11 | Admin view student statistics |  | 3 | 20 | 0 | Unstarted |  | 0
12 | Admin view student/tutor pairing history |  | 3 | 15 | 0 | Unstarted |  | 0
13 | Admin plan student lesson |  | 2 | 25 | 10 | Unstarted |  | 0
|  |  | Planned Total | 202 | 90 | Actual Total | 15 | 15

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Project Horseshoe Farm
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Allison Macdonald | 1,2,3,4,5,7,10 | 10 | N/A | N/A | 27 | 0 | 0 | 13.5 | 27.5 | 0 | 3 | 1 | 8 | 14.5 | 38.5
| John Carroll | 1,2,3,4,5,7,10 |  |  | 1,7,10 | 27 | 0 | 0 | 30 | 8.5 | 0 | 2 | 0 | 0 | 30 | 10.5
| Amanda Bailey | 1,4 |  |  | 1,2,7 | 27 | 0 | 0 | 7.25 | 19.5 | 0 | 1.25 | 0 | 0 | 7.25 | 20.75
| Cesar Sanchez | 1,2,3,4,5,7,10,12 |  |  | 1,10 | 27 |  | 0 |  | 7.5 |  | 0 |  | 0 | 0 | 7.5
| Lanxin (Mark) Ma | 1,2,10 |  |  | 1,2 | 27 | 0 | 0 | 7 | 16 | 0 | 1.5 | 1 | 0 | 8 | 17.5
[5 empty] | Totals | 135 | 0 | 0 | 57.75 | 79 | 0 | 7.75 | 2 | 8 | 51.75 | 77.25
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Set up team with WAMP/MAMP. Documentation. Presentation. Finished Story Boards. | [6 empty] | Get sponsor signature. Send prototype to sponsors. Get prototype hooked into database. Integrate embedded PDFs. Complete Cycle 2 user stories.
| Obstacles encountered since last status report: | [6 empty] | Notes:
MySQL randomly stopped working on Allison's machine.
Risks facing the project:
WHY WON'T OUR STUFF EVER WORK. Amanda's laptop died again :(

## Allison's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Allison
Week Ending: |  | 2016-03-07
Cycle: |  | Architectural Spike
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-01 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Met with team, set up localhost on each laptop, divided duties for cycle report.
Date: | 2016-03-02 | Result: | All members are outfitted with either WAMP or MAMP. The latest copy of code from Github has 404 errors.
Hours Worked: | 2.5 | Problems encountered: | WAMP doesn't work out of the box, relatives paths behaving strangely on virtual host
Day: | Thursday | Task(s) performed: | Research on relative pathing, working on written report
Date: | 2016-03-03 | Result: | Eventually set up virtual host directory correctly and fixed relative paths accordingly. Pushed to Github.
Hours Worked: | 2.5 | Problems encountered: | wampmysqld64 service will not start. Will be an issue as I start to work with MySQL.
Day: | Friday | Task(s) performed: | Met with Austin. Worked on Cycle Report.
Date: | 2016-03-04 | Result: | We'll be in touch with Austin if we run into any issues with SQL.
Hours Worked: | 2 | Problems encountered: | It would have been beneficial to start on this report earlier. Some people did not have enough time to have it finished early on Friday.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-03-05 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Corresponded with Austin about fixing MySQL error.
Date: | 2016-03-06 | Result: | Decided it would be best to re-install all of WAMP.
Hours Worked: | 1 | Problems encountered: | Problem unsolved.
Day: | Monday | Task(s) performed: | More work on front end prototype. Status report and team evaluation.
Date: | 2016-03-07 | Result: | Organized presentation.
Hours Worked: | 2 | Problems encountered: | Wish I had more time to code instead of documentation!!!!!!!

## Amanda's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Amanda
Week Ending: |  | 2016-03-07
Cycle: |  | SPIKE
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-01 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Meeting
Date: | 2016-03-02 | Result: | Got wamp installing properly on computer and was able to run the prototype
Hours Worked: | 2.5 | Problems encountered: | The CSS was not working
Day: | Thursday | Task(s) performed: | Wrote the system metaphor and sent out a onedrive word document for the report.
Date: | 2016-03-03 | Result: | Progress was made on the status report.
Hours Worked: | 1 | Problems encountered:
Day: | Friday | Task(s) performed: | Wrote the testing plan and procedures for the report
Date: | 2016-03-04 | Result: | Finished my part of the report
Hours Worked: | 2 | Problems encountered: | People had a hard time finishing their part on time.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-03-05 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | N/A
Date: | 2016-03-06 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Filled out timesheet for week for status report. Team meeting in order to organize presentation and deliverables.
Date: | 2016-03-07 | Result: | Status report was filled out.
Hours Worked: | 2.75 | Problems encountered:

## Cesar's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Cesar Sanchez
Week Ending: |  | 2016-03-07
Cycle: |  | SPIKE
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-01 | Result: | N/A
Hours Worked: | N/A | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Team meeting to discuss course of action for cycle report. Attempted to set up WAMP server on our computers.
Date: | 2016-03-02 | Result: | Installed WAMP on our computers and later got it working after some modifications. Duties for cycle report were determined
Hours Worked: | 2.5 | Problems encountered: | WAMP does not work out of the box and required several changes to get working properly.
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-03-03 | Result: | N/A
Hours Worked: | N/A | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Met with Allison to work on cycle report.
Date: | 2016-03-04 | Result: | Completed my section of the cycle report and assisted in preparing it to be sent to the sponsors
Hours Worked: | 2 | Problems encountered: | Not all members could get their sections completed due to busy schedules
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-03-05 | Result: | N/A
Hours Worked: | N/A | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Met with John to work on powerpoint presentation. Filled in status report.
Date: | 2016-03-06 | Result: | Got status report information filled in.
Hours Worked: | 3 | Problems encountered: | None
Day: | Monday | Task(s) performed:
Date: | 2016-03-07 | Result:
Hours Worked: |  | Problems encountered:

## Mark's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Lanxin (Mark) Ma
Week Ending: |  | 2016-03-07
Cycle: |  | SPIKE
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-01 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Meet with team to talk about course of action for cycle report. Attempted to set up wampserver to our computers.
Date: | 2016-03-02 | Result: | Got wampserver installed on our computers and cycle report duties were determined.
Hours Worked: | 2.5 | Problems encountered: | Had some initial trouble getting wampserver to work.
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-03-03 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Wrote the "user stories" and "lessons learned" part of the cycle report.
Date: | 2016-03-04 | Result: | Finished the "user stories" and "lessons learned" part of the cycle report.
Hours Worked: | 2 | Problems encountered: | Some people had difficulty completing their part for the status report on time.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-03-05 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | N/A
Date: | 2016-03-06 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Fill out status report and timesheet. Discussed and went through powerpoint presentation. Filled in peer evaluation document.
Date: | 2016-03-07 | Result: | Completed status report and timesheet. Each group member got assigned a part to talk about during the presentation.
Hours Worked: | 2.5 | Problems encountered: | None

## John's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | John Carroll
Week Ending: |  | 2016-03-07
Cycle: |  | Architectural Spike
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-01 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Met with team for normal meeting hours. Installed WAMP/MAMP across our laptops
Date: | 2016-03-02 | Result: | Setup for virtual servers
Hours Worked: | 4 | Problems encountered: | Ran into WAMP/MAMP path issues along with Github 404 errors
Day: | Thursday | Task(s) performed: | Developed cycle report documentation
Date: | 2016-03-03 | Result: | In the process of completing cycle report documentation.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Developed cycle report documentation. Also filled status report.
Date: | 2016-03-04 | Result: | We gave report to sponsor for signature
Hours Worked: | 9 | Problems encountered: | Lots to do.
Day: | Saturday | Task(s) performed: | Worked on weekly status report, and cycle report
Date: | 2016-03-05 | Result: | Progess achieved
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Worked on staus report, finalizing my sections of the cycle report. Then worked on the powerpoint presentation which is based off of the cycle report.
Date: | 2016-03-06 | Result: | Got to a finished presentation.
Hours Worked: | 10 | Problems encountered: | Group members were missing
Day: | Monday | Task(s) performed: | Finalize everything leading up to the project including the creation of the CD for cycle 1. We review and prep for Tuesday's presentation. Go over the demo. Assign slides and subject and run over the presentation.
Date: | 2016-03-07 | Result: | Prepped for presentation.
Hours Worked: | 3 | Problems encountered: | N/A