## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Project Horseshoe Farm | [6 empty] | Completed | 1
| Team Members: | Allison Macdonald, John Carroll, Amanda Bailey, Cesar Sanchez, Mark Ma | [6 empty] | Discarded | 2
| Date: | 2016-03-21 | Cycle: | Cycle 1 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | Horseshoe Farms has requested a webpage which can help streamline their online tutoring process. Students should be able to log into a website, see notifications, and navigate to tutoring materials easily. Notifications will include progress via horseshoes. Based on the day, either reading or math materials will be presented. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Begin communiction with database and get critical features functional.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Student Log In |  | 1 | 25 | 25 | Collaboration | 9 | 9
2 | Student View Notifications |  | 1 | 15 | 15 | Collaboration | 4 | 4
3 | Student Auto Redirect to Lesson |  | 1 | 10 | 5 | Collaboration |  | 0
4 | Student/Tutor start video chat service |  | 1 | 25 | 5 | Collaboration | 1 | 1
5 | Student view math worksheets |  | 1 | 10 | 10 | Collaboration |  | 0
6 | Student resume reading from last page |  | 2 | 12 | 0 | Unstarted |  | 0
7 | Student preview lesson for the day |  | 1 | 10 | 10 | Collaboration |  | 0
8 | Student/tutor screen share control |  | 2 | 10 | 0 | Unstarted |  | 0
9 | Tutor view daily schedule (student and lesson) |  | 1 | 15 | 0 | Unstarted |  | 0
10 | Secured log in |  | 1 | 10 | 10 | Collaboration | 1 | 1
11 | Admin view student statistics |  | 2 | 20 | 0 | Unstarted |  | 0
12 | Admin view student/tutor pairing history |  | 2 | 15 | 0 | Unstarted |  | 0
13 | Admin plan student lesson |  | 2 | 25 | 10 | Unstarted |  | 0
|  |  | Planned Total | 202 | 90 | Actual Total | 15 | 15

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Project Horseshoe Farm
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Allison Macdonald | 1,10 | 10 |  |  | 27 | 0 | 0 | 2.5 | 2.5 | 2 | 2 | 2.75 | 2.75 | 7.25 | 7.25
| John Carroll | 2,7,8,9 | 2 |  |  | 27 | 0 | 0 | 4.5 | 4.5 | 2 | 2 | 1 | 1 | 7.5 | 7.5
| Amanda Bailey | 1,4 |  |  | 1,2,7 | 27 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 4 | 4
| Cesar Sanchez | 1,5 |  |  | 1,2 | 27 |  |  | 2.5 | 2.5 | 2 | 2 | 0 | 0 | 4.5 | 4.5
| Lanxin (Mark) Ma | 1,2,10 |  |  | 1,2 | 27 | 0 | 0 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 2.5 | 2.5
[5 empty] | Totals | 135 | 0 | 0 | 14 | 14 | 8 | 8 | 3.75 | 3.75 | 23.25 | 23.25
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Clarifications on scope of project. Created a task board and used it. | [6 empty] | Log in with DB. Embedded PDFs (hopefully). Discover a method of integrating TeamViewer. Notifications integrated.
| Obstacles encountered since last status report: | [6 empty] | Notes:
| Spring Break. Scope creep - we have to make it clear that we need more time to develop than they think we do. | [6 empty] | N/A
Risks facing the project:
Tight schedule for implementing functionality.

## Allison's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Allison
Week Ending: |  | 2016-03-21
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Sent another email to sponsors concerning sponsor signature, played with MySQL
Date: | 2016-03-08 | Result: | N/A
Hours Worked: | 0.25 | Problems encountered: | I'll have to set up virtualhost again
Day: | Wednesday | Task(s) performed: | Split up tasks, began working on tasks
Date: | 2016-03-09 | Result: | Got a little familiar with PHPMyAdmin
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-03-10 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Met with sponsors, got clarification based on Cycle Report and Prototype.
Date: | 2016-03-11 | Result: | We have a better understanding of what the sponsors are looking for both visually and functionally.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-03-19 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Status meeting
Date: | 2016-03-20 | Result: | On the same page as everyone else.
Hours Worked: | 0.5 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Working with database and PHP
Date: | 2016-03-21 | Result: | More familiar with technologies
Hours Worked: | 2.5 | Problems encountered:

## Amanda's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Amanda
Week Ending: |  | 2016-03-21
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-08 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Team meeting. Split up tasks
Date: | 2016-03-09 | Result: | Now have a task page, to manage who is working on what.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-03-10 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Meeting with Dr. Dorsey, James, and Josh
Date: | 2016-03-11 | Result: | Now synchronized with the sponsor on how they want the site to work.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-03-19 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Status Meeting
Date: | 2016-03-20 | Result: | Filled out status report
Hours Worked: | 0.5 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Finished filling out timesheet
Date: | 2016-03-21 | Result: | A finished time sheet
Hours Worked: | 0.25 | Problems encountered: | N/A

## Cesar's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Cesar Sanchez
Week Ending: |  | 2016-03-07
Cycle: |  | SPIKE
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-01 | Result: | N/A
Hours Worked: | N/A | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Divided up tasks between members
Date: | 2016-03-02 | Result: | Members now have individual goals
Hours Worked: | 2 | Problems encountered: | None
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-03-03 | Result: | N/A
Hours Worked: | N/A | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Met weith sponsors to get more info and clarifications
Date: | 2016-03-04 | Result: | We have a better idea of their exact requirements, letting us make a plan
Hours Worked: | 2 | Problems encountered: | There is a lot for us to do
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-03-05 | Result: | N/A
Hours Worked: | N/A | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Status meeting
Date: | 2016-03-06 | Result: | We know where we stand
Hours Worked: | 0.5 | Problems encountered: | Morale
Day: | Monday | Task(s) performed:
Date: | 2016-03-07 | Result:
Hours Worked: |  | Problems encountered:

## Mark's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Lanxin (Mark) Ma
Week Ending: |  | 2016-03-21
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-08 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Meet with team to split up tasks.
Date: | 2016-03-09 | Result: | Each team member were assigned tasks, so they will have goals.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-03-10 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | N/A
Date: | 2016-03-11 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | I was unable to attend the meeting due to an interview.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-03-12 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | N/A
Date: | 2016-03-20 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | Unable to make it to status meeting due to delayed arrival at Auburn.
Day: | Monday | Task(s) performed: | Fill out status report and timesheet.
Date: | 2016-03-21 | Result: | Completed status report and timesheet.
Hours Worked: | 0.5 | Problems encountered: | None

## John's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | John Carroll
Week Ending: |  | 2016-03-21
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-08 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Created a task board and used it to assign tasks to team members.
Date: | 2016-03-09 | Result: | Became more efficient.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | Developed cycle report documentation.
Date: | 2016-03-10 | Result: | In the process of completing cycle report documentation.
Hours Worked: | 0 | Problems encountered: | N/A.
Day: | Friday | Task(s) performed: | Developed cycle report documentation. Also filled status report.
Date: | 2016-03-11 | Result: | Acquired update and sponsor signature.
Hours Worked: | 2 | Problems encountered: | Lots to do.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-03-12 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Status Report filling out, looked at the product code for my user stories.
Date: | 2016-03-20 | Result: | Filled out status report with team.
Hours Worked: | 3 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Finalize status report.
Date: | 2016-03-21 | Result: | Submitted report
Hours Worked: | 0.5 | Problems encountered: | N/A