## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Project Horseshoe Farm | [6 empty] | Completed | 1
| Team Members: | Allison Macdonald, John Carroll, Amanda Bailey, Cesar Sanchez, Mark Ma | [6 empty] | Discarded | 2
| Date: | 2016-03-28 | Cycle: | Cycle 1 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | Horseshoe Farms has requested a webpage which can help streamline their online tutoring process. Students should be able to log into a website, see notifications, and navigate to tutoring materials easily. Notifications will include progress via horseshoes. Based on the day, either reading or math materials will be presented. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Begin communiction with database and get critical features functional.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Student Log In |  | 1 | 25 | 25 | Collaboration | 9 | 9
2 | Student View Notifications |  | 1 | 15 | 15 | Collaboration | 4 | 4
3 | Student Auto Redirect to Lesson |  | 1 | 10 | 5 | Collaboration |  | 0
4 | Student/Tutor start video chat service |  | 1 | 25 | 5 | Collaboration | 1 | 1
5 | Student view math worksheets |  | 1 | 10 | 10 | Collaboration |  | 0
6 | Student resume reading from last page |  | 2 | 12 | 0 | Unstarted |  | 0
7 | Student preview lesson for the day |  | 1 | 10 | 10 | Collaboration |  | 0
8 | Student/tutor screen share control |  | 2 | 10 | 0 | Unstarted |  | 0
9 | Tutor view daily schedule (student and lesson) |  | 1 | 15 | 0 | Unstarted |  | 0
10 | Secured log in |  | 1 | 10 | 10 | Collaboration | 4 | 4
11 | Admin view student statistics |  | 2 | 20 | 0 | Unstarted |  | 0
12 | Admin view student/tutor pairing history |  | 2 | 15 | 0 | Unstarted |  | 0
13 | Admin plan student lesson |  | 2 | 25 | 10 | Unstarted |  | 0
|  |  | Planned Total | 202 | 90 | Actual Total | 18 | 18

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Project Horseshoe Farm
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Allison Macdonald | 8 | 1,10 |  |  | 27 |  | 0 | 2 | 3.5 | 2 | 4 | 5.25 | 6 | 9.25 | 13.5
| John Carroll | 2,7,8,9 | 2 |  |  | 27 | 0 | 0 | 4.5 | 9 | 2 | 4 | 1 | 2 | 7.5 | 15
| Amanda Bailey | 8 |  |  |  | 27 | 0 | 0 | 4.25 | 9.25 | 2 | 4 | 2 | 2 | 8.25 | 11.75
| Cesar Sanchez | 8 |  |  |  | 27 |  |  | 1.5 | 4 | 2 | 4 | 0 | 0 | 3.5 | 8
| Lanxin (Mark) Ma | 1,2,10 |  |  | 1,2 | 27 | 0 | 0 | 2 | 6.5 | 2 | 4 | 1 | 1 | 5 | 11.5
[5 empty] | Totals | 135 | 0 | 0 | 14.25 | 32.25 | 10 | 20 | 9.25 | 11 | 28.5 | 48.25
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| We now have a clearer idea of our sponsors' goals. We have solved the issues we were having when attempting to talk with the MySQL database. Thanks to collaborating with Austin Hancock, we are now able to run queries using PHP to MySQL. | [6 empty] | Student auto redirect to lesson, start video chat service, tutor views daily schedule, look into development on GoDaddy
| Obstacles encountered since last status report: | [6 empty] | Notes:
| Time was an issue due to course assignments and tests during this week. | [6 empty] | We need to work in separation of our "Tutor" user into "Team Leader" and just "Tutor". This is something we learned upon further clarification with out sponsor.
Risks facing the project:
Crunch week! All members are very busy!

## Allison's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Allison
Week Ending: |  | 2016-03-21
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-22 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Met with team, generated ideas on launching TeamViewer
Date: | 2016-03-23 | Result: | Decided on a batch file for launching both TeamViewer and webpage.
Hours Worked: | 1 | Problems encountered: | Cannot launch .exe from webpage for security reasons
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-03-24 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Met with Austin, worked out PHP issues. Met with James and Dr. Doresey.
Date: | 2016-03-25 | Result: | Talking to database. Established semester goals with sponsors.
Hours Worked: | 2 | Problems encountered:
Day: | Saturday | Task(s) performed: | Validate user password with expected password and redirect if correct.
Date: | 2016-03-26 | Result: | Validates correctly.
Hours Worked: | 3.25 | Problems encountered: | Will not stay on page if password invalid.
Day: | Sunday | Task(s) performed: | Met with team
Date: | 2016-03-27 | Result: | Finished status report and split up tasks for next week.
Hours Worked: | 1 | Problems encountered: | Members missing
Day: | Monday | Task(s) performed: | Finished login functionality complete with error messages and redirecting.
Date: | 2016-03-28 | Result: | Finished user story!
Hours Worked: | 2 | Problems encountered: | PHP specific syntax, learning about sessions.

## Amanda's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Amanda
Week Ending: |  | 2016-03-28
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Researched methods for TeamViewer. Installed WAMP onto computer.
Date: | 2016-03-22 | Result: | Thought of a method for incorporating TeamViewer.
Hours Worked: | 2 | Problems encountered: | WAMP not working correctly. Encountering an error that says it is not connected to the DNS server.
Day: | Wednesday | Task(s) performed: | Team meeting: Looked at possible options for Teamviewer.
Date: | 2016-03-23 | Result: | Decision was made to pursure the option of creating a batch that will launch the website login page and TeamViewer.
Hours Worked: | 1.25 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | Sent an email to the Project Horseshoe Farm, asking them if all the Windows machines they use are all Windows 10, and if they use one TeamViewer account for all students. Changed the default browser for WAMP from Chrome to Firefox
Date: | 2016-03-24 | Result: | Now know that they use mostly Windows 8 and some Windows 10.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Meeting wtith Austion. Meeting with James and Dr. Dorsey. Team meeting after sponser meeting.
Date: | 2016-03-25 | Result: | PHP is now setup up Allison's computer.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-03-26 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Status Meeting
Date: | 2016-03-27 | Result: | Filled out status report, split tasks
Hours Worked: | 1 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | N/A
Date: | 2016-03-28 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A

## Cesar's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Cesar Sanchez
Week Ending: |  | 2016-03-07
Cycle: |  | SPIKE
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-22 | Result: | N/A
Hours Worked: | N/A | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Met with team to address the Teamviewer question
Date: | 2016-03-23 | Result: | Decided that launching teamviewer and a browser might only be realistically attainable via a batch file
Hours Worked: | 1 | Problems encountered: | Browser cannot natively launch an exe due to security reasons. The password to connect to a teamviewer account changes every time, so we need a way to get that password to the tutor without student input and automatically log in the student
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-03-24 | Result: | N/A
Hours Worked: | N/A | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Meeting with Austin and sponsors, team meeting
Date: | 2016-03-25 | Result: | PHP issues resolved, started planning a trip to horseshoe farm
Hours Worked: | 2 | Problems encountered: | Some connectionissues during video call
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-03-26 | Result: | N/A
Hours Worked: | N/A | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | N/A
Date: | 2016-03-27 | Result: | N/A
Hours Worked: | N/A | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Filled out Time Sheet
Date: | 2016-03-28 | Result: | Time sheet got filled out
Hours Worked: | 0.5 | Problems encountered: | None

## Mark's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Lanxin (Mark) Ma
Week Ending: |  | 2016-03-28
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-22 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Met with team. Looked at options for Teamviewer
Date: | 2016-03-23 | Result: | Decided on creating a batch file for Teamviewer.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-03-24 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Met with Austin and the sponsors James and Dr. Dorsey. Allison got PHP issues worked out.
Date: | 2016-03-25 | Result: | Allison got PHP installed on her computer. Group established goals for the rest of spring semester as well as the summer semester.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-03-26 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Reinstalled WAMP onto my computer.
Date: | 2016-03-27 | Result: | WAMP got reinstalled.
Hours Worked: | 1.5 | Problems encountered: | Still cannot get WAMP to work on my computer. Cannot get WAMP connected on my PC.
Day: | Monday | Task(s) performed: | Fill out status report and timesheet.
Date: | 2016-03-28 | Result: | Completed status report and timesheet.
Hours Worked: | 1 | Problems encountered: | None

## John's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | John Carroll
Week Ending: |  | 2016-03-28
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-22 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Met with group.
Date: | 2016-03-23 | Result: | Became more efficient.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | Developed cycle report documentation.
Date: | 2016-03-24 | Result: | In the process of completing cycle report documentation.
Hours Worked: | 0 | Problems encountered: | N/A.
Day: | Friday | Task(s) performed: | Austin helped our group out with PHP/MySQL. VIdeo conference with James Friedman and later, Dr. Dorsey.
Date: | 2016-03-25 | Result: | Made significant progress.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-03-26 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Status Report filling out, reorganized priorities based off of progress with user stories.
Date: | 2016-03-27 | Result: | Filled out status report with team.
Hours Worked: | 3 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Finalize status report.
Date: | 2016-03-28 | Result: | Submitted report
Hours Worked: | 0.5 | Problems encountered: | N/A