## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Project Horseshoe Farm | [6 empty] | Completed | 1
| Team Members: | Allison Macdonald, John Carroll, Amanda Bailey, Cesar Sanchez, Mark Ma | [6 empty] | Discarded | 2
| Date: | 2016-04-04 | Cycle: | Cycle 1 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | Horseshoe Farms has requested a webpage which can help streamline their online tutoring process. Students should be able to log into a website, see notifications, and navigate to tutoring materials easily. Notifications will include progress via horseshoes. Based on the day, either reading or math materials will be presented. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Begin communiction with database and get critical features functional.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Student Log In |  | 1 | 25 | 25 | Completed | 9 | 9
2 | Student View Notifications |  | 1 | 15 | 15 | Completed | 6 | 10
3 | Student Auto Redirect to Lesson |  | 1 | 10 | 5 | Completed | 5 | 5
4 | Student/Tutor start video chat service |  | 1 | 25 | 5 | Collaboration | 1 | 1
5 | Student view math worksheets |  | 1 | 10 | 10 | Completed | 3 | 3
6 | Student resume reading from last page |  | 2 | 12 | 0 | Unstarted | 0 | 0
7 | Student preview lesson for the day |  | 1 | 10 | 10 | Discarded | 0 | 0
8 | Student/tutor screen share control |  | 2 | 10 | 0 | Collaboration | 2 | 2
9 | Tutor view daily schedule (student and lesson) |  | 1 | 15 | 0 | Collaboration | 3.25 | 3.25
10 | Secured log in |  | 1 | 10 | 10 | Completed | 4 | 4
11 | Admin view student statistics |  | 2 | 20 | 0 | Discarded | 0 | 0
12 | Admin view student/tutor pairing history |  | 2 | 15 | 0 | Discarded | 0 | 0
13 | Admin plan student lesson |  | 2 | 25 | 10 | Unstarted | 0 | 0
|  |  | Planned Total | 202 | 90 | Actual Total | 33.25 | 37.25

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Project Horseshoe Farm
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Allison Macdonald | 3 | 3, 5 | 1,8,5 | 1,2,5,8 | 27 | 4 | 4 | 1.75 | 5.25 | 5 | 9 | 2 | 8 | 12.75 | 26.25 | Also travelled for 6 more hrs.
| John Carroll | 2 | 2 | 2 | 1,2,5,8 | 27 | 0 | 0 | 9.25 | 18.25 | 2 | 6 | 6 | 8 | 17.25 | 32.25
| Amanda Bailey | 9 | 9 |  | 1,2,5,8 | 27 | 0 | 0 | 7.25 | 16.5 | 0 | 4 | 3.25 | 5.25 | 10.5 | 25.75
| Cesar Sanchez | 5 | 5 | 5 | 5 | 27 | 0 | 0 | 2 | 2 | 5 | 9 | 5 | 5 | 12 | 16
| Lanxin (Mark) Ma | 1 | 1 | 1 | 1 | 27 | 0 | 0 | 3 | 6 | 9 | 9 | 2 | 2 | 14 | 17
[5 empty] | Totals | 135 | 4 | 4 | 23.25 | 48 | 21 | 37 | 18.25 | 28.25 | 52.5 | 100.25
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Our demo's expectations are now being met. Demo requirements being: "Student login, redirection to lesson, and math worksheets." | [6 empty] | Get sponsor's feedback regarding upgrading hosting package from economy to deluxe. Work on CSS for web component. Re-assign user stories and work towards completing the uncompleted user stories.
| Obstacles encountered since last status report: | [6 empty] | Notes:
| Lack of time due to other academic obligations. | [6 empty] | Talk to Dr.Chapman regarding a possible summer research group opportunity surrounding this remote tutoring web component for Project HSF.
Risks facing the project:
Not being usable by summer.

## Allison's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Allison
Week Ending: |  | 2016-04-04
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-29 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Drove out to Greensboro to observe tutoring.
Date: | 2016-03-30 | Result: | Much better understanding.
Hours Worked: | 5 | Problems encountered: | Spent an entire day driving!
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-03-31 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Wrote on cycle report.
Date: | 2016-04-01 | Result: | Some data written for cycle report.
Hours Worked: | 0.25 | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | Worked on cycle report. Collaborated with Cesar on PDF.
Date: | 2016-04-02 | Result: | PDF integration functional.
Hours Worked: | 4.5 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Merge separate functionalities into master branch. Collaborated with Amanda on PHP. Refactor code, make modifications.
Date: | 2016-04-03 | Result: | Cycle report section finished, demo ready for Tuesday.
Hours Worked: | 6 | Problems encountered: | Minor bugs
Day: | Monday | Task(s) performed: | Work on presentation and filled out peer evaluations.
Date: | 2016-04-04 | Result: | Presentation finished except for one slide.
Hours Worked: | 1.25 | Problems encountered:

## Amanda's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Amanda
Week Ending: |  | 2016-04-04
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-29 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Started working on tutor pages
Date: | 2016-03-30 | Result: | Better understaning of html and css
Hours Worked: | 1 | Problems encountered: | Inexperience with web developement slowed the productivity
Day: | Thursday | Task(s) performed: | worked on tutor pages. Made a cycle 2 report word document and shared it with the team. Started working on System Metaphor as well as Test Plan and Procedures.
Date: | 2016-03-31 | Result: | There is a shared location to collaborate on the cycle 2 report. Finished a hard coded version of the tutor pages. Tutor can now login as "bob" with the password "tutor" and be redirected to a welcome page.
Hours Worked: | 3 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Attempted to review secured login and student login that is connected to the database.
Date: | 2016-04-01 | Result: | N/A
Hours Worked: | 0.25 | Problems encountered: | Got an error.
Day: | Saturday | Task(s) performed: | Created a cycle 2 report correspondance page and shared it with the team. Worked on System Metaphor as well as Test Plan and Precdures
Date: | 2016-04-02 | Result: | Finished system metaphor. There is now a shared location for cycle 2 corresponance
Hours Worked: | 0.5 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Was taught how to create a database and then created one. Finished the Test Plan and Procedures. Started presentation. Reviewed the use cases that have been done.
Date: | 2016-04-03 | Result: | Finished my part of the cycle report. Have a framework done for the presentation
Hours Worked: | 5 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Team meeting - finished presentation. Finished timesheet and peer evals
Date: | 2016-04-04 | Result:
Hours Worked: | 0.75 | Problems encountered:

## Cesar's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Cesar Sanchez
Week Ending: |  | 2016-04-04
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-29 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Traveled to Greensboro to see the day-to-day operations at horseshoe farms firsthand
Date: | 2016-03-30 | Result: | Got a firsthand look at how a typical tutoring session goes at Horsesho farm
Hours Worked: | 5 | Problems encountered: | Note that we also had a total of six hours of travel time in addition to the five hours spent at HSF. Not sure if these hours (which were technically dedicated to the project) count or not, but thought they deserved a mention
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-03-31 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Developed the PDF functionality
Date: | 2016-04-01 | Result: | PDF code was developed, if only for a standalone HTML page
Hours Worked: | 2 | Problems encountered: | Inexperience with HTML
Day: | Saturday | Task(s) performed: | Met with Allison to integrate PDF functionality in the website
Date: | 2016-04-02 | Result: | PDF was successfully integrated into the website
Hours Worked: | 3 | Problems encountered: | Figuring out how to make JavaScript, PHP, and HTML to ALL play nice together
Day: | Sunday | Task(s) performed: | Worked on cycle report
Date: | 2016-04-03 | Result: | My section of the cycle report was completed
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Monday | Task(s) performed:
Date: | 2016-04-04 | Result:
Hours Worked: |  | Problems encountered:

## Mark's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Lanxin (Mark) Ma
Week Ending: |  | 2016-04-04
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-29 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | N/A
Date: | 2016-03-30 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | Unable to go on sponsor trip due to interfering personal business.
Day: | Thursday | Task(s) performed: | Worked on php code for unsecured student login using notepad++
Date: | 2016-03-31 | Result: | Got part of unsecured student login code written in notepad++
Hours Worked: | 2 | Problems encountered: | Unable to run code for unsecured student login
Day: | Friday | Task(s) performed: | Meet with Mr. Hancock to discuss project. Got the graded evaluation rubric for the cycle 1 report from Dr. Chapman. Tried to get the code for unsecured student login to work on notepad++.
Date: | 2016-04-01 | Result: | Obtained evaluation rubric from Dr. Chapman.
Hours Worked: | 2 | Problems encountered: | Still cannot get unsecured student login code to work on notepad++.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-04-02 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Proofread and edited user stories and lessons learned section in cycle 2 report. Filled out status report and timesheet.
Date: | 2016-04-03 | Result: | User stories and lessons learned section of cycle report finalized. Status report and timesheet filled out.
Hours Worked: | 5 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Worked on presentations and peer evaluations.
Date: | 2016-04-04 | Result: | Decided on who's going to print what and filled out peer evaluations.
Hours Worked: | 2 | Problems encountered: | N/A

## John's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | John Carroll
Week Ending: |  | 2016-04-04
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-03-29 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | N/A
Date: | 2016-03-30 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-03-31 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Met with Austin, worked on cycle report. Called Godaddy in regards to hosting plans and our component's intent's capabilities.
Date: | 2016-04-01 | Result: | Got some info written for cycle report. As well as some important info.
Hours Worked: | 2.25 | Problems encountered: | Not sure of what is to come given the technologies and given the time to test said technologies.
Day: | Saturday | Task(s) performed: | Worked on Student View Notifications and Login pages's CSS.
Date: | 2016-04-02 | Result: | PDF integration functional.
Hours Worked: | 6 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Worked on cycle 2 report, status report for week 3,
Date: | 2016-04-03 | Result: | Demo ready for Tuesday, work is near complete on the deliverables.
Hours Worked: | 6 | Problems encountered: | Minor bugs in the demo.
Day: | Monday | Task(s) performed: | Work on finalizing cycle 2 deliverables.
Date: | 2016-04-04 | Result: | Finished cycle 2's deliverables.
Hours Worked: | 3 | Problems encountered: | N/A