## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Project Horseshoe Farm | [6 empty] | Completed | 1
| Team Members: | Allison Macdonald, John Carroll, Amanda Bailey, Cesar Sanchez, Mark Ma | [6 empty] | Discarded | 2
| Date: | 2016-04-11 | Cycle: | Cycle 2 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | Horseshoe Farms has requested a webpage which can help streamline their online tutoring process. Students should be able to log into a website, see notifications, and navigate to tutoring materials easily. Notifications will include progress via horseshoes. Based on the day, either reading or math materials will be presented. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Integrate functionality with external components and move to GoDaddy.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Student Log In |  | 1 | 25 | 25 | Completed | 9 | 9
2 | Student View Notifications |  | 1 | 15 | 15 | Completed | 6 | 10
3 | Student Auto Redirect to Lesson |  | 1 | 10 | 5 | Completed | 5 | 5
4 | Student/Tutor start video chat service |  | 1 | 25 | 5 | Collaboration | 1 | 1
5 | Student view math worksheets |  | 1 | 10 | 10 | Completed | 3 | 3
6 | Student resume reading from last page |  | 2 | 12 | 0 | Unstarted | 0 | 0
7 | Student preview lesson for the day |  | 1 | 10 | 10 | Discarded | 0 | 0
8 | Student/tutor screen share control |  | 2 | 10 | 0 | Collaboration | 2 | 2
9 | Tutor view daily schedule (student and lesson) |  | 1 | 15 | 0 | Discarded | 3.25 | 3.25
10 | Secured log in |  | 1 | 10 | 10 | Completed | 4 | 4
11 | Admin view student statistics |  | 2 | 20 | 0 | Discarded | 0 | 0
12 | Admin view student/tutor pairing history |  | 2 | 15 | 0 | Discarded | 0 | 0
13 | Team leader plan student lesson |  | 2 | 25 | 10 | Unstarted | 0 | 0
14 | Auto login into external websites |  | 2 | 18 | 18 | Collaboration | 2.5 | 2.5
15 | Admin pair student-tutor |  | 2 | 15 | 15 | Collaboration | 4 | 4
16 | Tutor Waiting View |  | 2 | 15 | 15 | Collaboration | 0 | 0
|  |  | Planned Total | 235 | 123 | Actual Total | 35.75 | 39.75

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Project Horseshoe Farm
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Allison Macdonald | 4. 14 | 15 |  |  | 27 | 0 | 0 | 2 | 2 | 1 | 1 | 3 | 3 | 6 | 6
| John Carroll | 14 |  |  |  | 27 | 0 | 0 | 2.4 | 2.4 | 0 | 0 | 0 | 0 | 2.4 | 2.4
| Amanda Bailey | 8 |  |  |  | 27 | 0 | 0 | 2 | 2 | 1 | 1 | 0.25 | 0.25 | 3.25 | 3.25
| Cesar Sanchez | 4, 13, 15 |  |  |  | 27 | 0 | 0 | 0.25 | 0.25 | 1 | 1 | 2.5 | 2.5 | 3.75 | 3.75
| Lanxin (Mark) Ma | 4 |  |  |  | 27 | 0 | 0 | 2 | 2 | 1 | 1 | 0.5 | 0.5 | 3.5 | 3.5
[5 empty] | Totals | 135 | [8 empty] | 15.4 | 15.4
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Redefined user stories. Held a phone conference with sponsor. Began implementing student-tutor matching page. Began tutor waiting page. Pros and cons research on alternatives to TeamViewer. | [6 empty] | Finish student-tutor pairing page and auto-login to external webpage.
| Obstacles encountered since last status report: | [6 empty] | Notes:
Addtitions to user stories and re-prioritization of user stories.
Risks facing the project:
Lack of time to fulfill all of the customers wants and needs.

## Allison's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Allison
Week Ending: |  | 2016-04-11
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-04-04 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Met with team, began work on student-tutor matching page.
Date: | 2016-04-05 | Result: | We have a dynamically populated table of students.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-04-06 | Result: | N/A
Hours Worked: |  | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Met with Dr. Dorsey
Date: | 2016-04-07 | Result: | Further clarifications on requirements
Hours Worked: | 1 | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-04-08 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Worked on student-tutor pairing. Met with team to re-assign user stories based on new priorities.
Date: | 2016-04-09 | Result: | Better understanding of what will be accomplished this week.
Hours Worked: | 2.5 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Worked on student-tutor pairing.
Date: | 2016-04-10 | Result: | Progress
Hours Worked: | 0.5 | Problems encountered: | jQuery

## Amanda's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Amanda
Week Ending: |  | 2016-04-11
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-04-04 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Team Meeting. Worked on TeamViewer pros and cons table
Date: | 2016-04-05 | Result: | started a pros and cons table for alternative implementations for TeamViewer
Hours Worked: | 1.25 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-04-06 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Met with sponsor
Date: | 2016-04-07 | Result: | tasks reprioritized
Hours Worked: | 1 | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-04-08 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Team Meeting worked on weekly status report. assigned tasks for the week
Date: | 2016-04-09 | Result: | Have the task of working on auto login to external websites
Hours Worked: | 1 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | N/A
Date: | 2016-04-10 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A

## Cesar's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Cesar Sanchez
Week Ending: |  | 2016-04-11
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-04-04 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Team meeting
Date: | 2016-04-05 | Result: | Student table dynamically populates
Hours Worked: | 2 | Problems encountered: | None
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-04-06 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Video call with Dr. Dorsey
Date: | 2016-04-07 | Result: | Requirements clarification
Hours Worked: | 1 | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-04-08 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Filled in Time sheet
Date: | 2016-04-09 | Result: | Time sheet was filled in
Hours Worked: | 0.25 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Worked on student-tutor scheduling page
Date: | 2016-04-10 | Result: | Made progress on implementation
Hours Worked: | 0.5 | Problems encountered: | Strange Jquery issues

## Mark's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Lanxin (Mark) Ma
Week Ending: |  | 2016-04-11
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-04-04 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Met with team. Discussed about plans for cycle 3.
Date: | 2016-04-05 | Result: | Final cycle planned out.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-04-06 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Met with Mr. Hancock. Met with Dr. Dorsey.
Date: | 2016-04-07 | Result: | Requirements further clarified.
Hours Worked: | 1 | Problems encountered: | Had to leave early for Birmingham during the sponsor meeting.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-04-08 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | N/A
Date: | 2016-04-09 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | Unable to attend group meeting due to being out of town.
Day: | Monday | Task(s) performed: | Fill out status report and timesheet.
Date: | 2016-04-10 | Result: | Status report and timesheet filled out.
Hours Worked: | 0.5 | Problems encountered: | N/A

## John's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | John Carroll
Week Ending: |  | 2016-04-11
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-04-04 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Talked about godaddy hosting, getting our component on the website, and how it should be a part of a user story.
Date: | 2016-04-05 | Result: | Planned out this final cycle.
Hours Worked: | 1.25 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-04-06 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | Job interviews in FL
Day: | Friday | Task(s) performed: | N/A
Date: | 2016-04-07 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | Job interviews in FL
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-04-08 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Sunday Stand-up meeting, got briefed on Friday's meeting while I was away.
Date: | 2016-04-09 | Result: | Got up to speed.
Hours Worked: | 1.15 | Problems encountered:
Day: | Monday | Task(s) performed: | N/A
Date: | 2016-04-10 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A