## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Project Horseshoe Farm | [6 empty] | Completed | 1
| Team Members: | Allison Macdonald, John Carroll, Amanda Bailey, Cesar Sanchez, Mark Ma | [6 empty] | Discarded | 2
| Date: | 2016-04-18 | Cycle: | Cycle 2 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | Horseshoe Farms has requested a webpage which can help streamline their online tutoring process. Students should be able to log into a website, see notifications, and navigate to tutoring materials easily. Notifications will include progress via horseshoes. Based on the day, either reading or math materials will be presented. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Integrate functionality with external components and move to GoDaddy.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Student Log In |  | 1 | 25 | 25 | Completed | 9 | 9
2 | Student View Notifications |  | 1 | 15 | 15 | Completed | 6 | 10
3 | Student Auto Redirect to Lesson |  | 1 | 10 | 5 | Completed | 5 | 5
4 | Student/Tutor start video chat service |  | 1 | 25 | 5 | Collaboration | 1 | 1
5 | Student view math worksheets |  | 1 | 10 | 10 | Completed | 3 | 3
6 | Student resume reading from last page |  | 2 | 12 | 0 | Unstarted | 0 | 0
7 | Student preview lesson for the day |  | 1 | 10 | 10 | Discarded | 0 | 0
8 | Student/tutor screen share control |  | 2 | 10 | 0 | Discarded | 2 | 2
9 | Tutor view daily schedule (student and lesson) |  | 1 | 15 | 0 | Discarded | 3.25 | 3.25
10 | Secured log in |  | 1 | 10 | 10 | Completed | 4 | 4
11 | Admin view student statistics |  | 2 | 20 | 0 | Discarded | 0 | 0
12 | Admin view student/tutor pairing history |  | 2 | 15 | 0 | Discarded | 0 | 0
13 | Team leader plan student lesson |  | 2 | 25 | 10 | Unstarted | 0 | 0
14 | Auto login into external websites |  | 2 | 18 | 18 | Collaboration | 3 | 3
15 | Admin pair student-tutor |  | 2 | 15 | 15 | Completed | 15 | 15
16 | Tutor Waiting View |  | 2 | 15 | 15 | Collaboration | 3.75 | 3.75
17 | Log-out/Auto log-out |  | 2
|  |  | Planned Total | 235 | 123 | Actual Total | 36.25 | 40.25

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Project Horseshoe Farm
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Allison Macdonald | 4, 16, 17 | 15, 16 | 16 | 15, 16 | 27 | 0 | 0 | 6 | 7 | 1 | 2 | 6.5 | 9.5 | 13.5 | 18.5
| John Carroll | 14 |  |  |  | 27 | 0 | 0 | 8 | 10.4 | 1 | 1 | 0 | 0 | 9 | 11.4
| Amanda Bailey | 14, 16 | 16 |  |  | 27 | 1 | 0 | 3 | 5 | 1 | 1 | 1.25 | 1.5 | 6.25 | 7.5
| Cesar Sanchez | 4, 13, 15 |  |  |  | 27 |  | 0 | 0.25 | 0.5 | 1 | 2 | 1.5 | 2.5 | 2.75 | 5
| Lanxin (Mark) Ma | 16 |  |  |  | 27 | 1 | 0 | 2.5 | 4 | 1 | 2 | 0.25 | 0.5 | 4.75 | 6.5
[5 empty] | Totals | 135 | [8 empty] | 31.5 | 42.4
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Student-Tutor pairing page, moved to x10 to unify database and host on a site accessible to our sponsors, further clarification concerning admin's connect functionality. Finished Tutor waiting page. | [6 empty] | Team leader makes recommendations(13), create database for launching talky.io (4)
| Obstacles encountered since last status report: | [6 empty] | Notes:
WAMP crashed prior to demo -> had to describe visuals during phone call. Auto-login for both Chromebook and PC.
Risks facing the project:
User story #8 was dropped due to the amount of risk we faced with potentially not being able to finish it. After talking with our sponsors, they agreed to drop it, mostly in part to them explicitly saying that screen sharing is more important to them than screen control/remote desktop features.

## Allison's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Allison
Week Ending: |  | 2016-04-18
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Worked on student-tutor pairing page.
Date: | 2016-04-12 | Result: | Student check-in/out communicates with database and refresh button for remote tutors implemented.
Hours Worked: | 1.5 | Problems encountered: | Must find a way to store student id somewhere in table.
Day: | Wednesday | Task(s) performed: | N/A
Date: | 2016-04-13 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | Finished functionality of student-tutor pairing page.
Date: | 2016-04-14 | Result: | Everything is smoothly connecting to the database and UI behaves as expected.
Hours Worked: | 3.5 | Problems encountered: | Need some CSS tweaks to be more usable.
Day: | Friday | Task(s) performed: | Met with sponsors, met with Austin. Worked with Austin on migrating to x10.
Date: | 2016-04-15 | Result: | Centralized database, clearer specifications, webpage is somewhere where sponsors can interact with it.
Hours Worked: | 5 | Problems encountered: | Migrating to x10 had its own set of special problems.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-04-16 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Met with team, worked with Amanda to complete tutor waiting page
Date: | 2016-04-17 | Result: | Tutor waiting page finished
Hours Worked: | 3.5 | Problems encountered: | Minor PHP errors, team is paniking.
Day: | Monday | Task(s) performed: | N/A
Date: | 2016-04-18 | Result: | N/A
Hours Worked: |  | Problems encountered: | N/A

## Amanda's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Amanda
Week Ending: |  | 2016-04-18
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Looked into the option Austin gave us for auto login to external websites. Sent email to Austin. Looked into the second option Austin provided, have yet to implement it
Date: | 2016-04-12 | Result: | Marked off a method as being a suitable method
Hours Worked: | 0.5 | Problems encountered: | finding a suitable auto login method for external websites
Day: | Wednesday | Task(s) performed: | Team Meeting. Discussed user stories.
Date: | 2016-04-13 | Result: | Made a plan
Hours Worked: | 0.75 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | Refactored tutor pages to be more in line with what is desired
Date: | 2016-04-14 | Result: | removed welcome page for tutor and login credentials are now pulled from the database for the tutor.
Hours Worked: | 1 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Meeting with Austin. Meeting with James, Josh, and Dr. Dorsey.
Date: | 2016-04-15 | Result: | Received more clarifactiaon on what the sponsors want.
Hours Worked: | 1.25 | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-04-16 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Team Meeting. Met with Allison to work on merging the tutor portion with the rest of the project.
Date: | 2016-04-17 | Result: | Status report filled out
Hours Worked: | 2.25 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | N/A
Date: | 2016-04-17 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A

## Cesar's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Cesar Sanchez
Week Ending: |  | 2016-04-11
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-04-12 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | N/A
Date: | 2016-04-13 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | None
Day: | Thursday | Task(s) performed: | Completed student-tutor pairing page
Date: | 2016-04-14 | Result: | Page is functional and updates the database accordingly
Hours Worked: | 3.5 | Problems encountered: | Could be made prettier/more user-friendly
Day: | Friday | Task(s) performed: | Video call with sponsors. Discussed some topics
Date: | 2016-04-15 | Result: | Requirements clarification
Hours Worked: | 1 | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-04-16 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Group meeting, discusses user stories to work on during the coming week
Date: | 2016-04-17 | Result: | User stories to work on have been assigned
Hours Worked: | 1 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Filled in time sheet
Date: | 2016-04-18 | Result: | Time sheet got filled
Hours Worked: | 0.25 | Problems encountered: | N/A

## Mark's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Lanxin (Mark) Ma
Week Ending: |  | 2016-04-11
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-04-12 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Met with team. Discussed about user stories
Date: | 2016-04-13 | Result: | Final cycle planned out.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-04-14 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Met with Mr. Hancock. Met with Dr. Dorsey.
Date: | 2016-04-15 | Result: | Requirements further clarified. Hancock got some database issues fixed.
Hours Worked: | 1.25 | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-04-16 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Attended group meeting. Planned out who is doing what user stories. Filled out status report and timesheet.
Date: | 2016-04-17 | Result: | Each group member got assigned different user stories. Status report and timesheet filled out.
Hours Worked: | 1.25 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Fixed status report and timesheet.
Date: | 2016-04-18 | Result: | Status report and timesheet revised.
Hours Worked: | 0.25 | Problems encountered: | N/A

## John's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | John Carroll
Week Ending: |  | 2016-04-18
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-04-12 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Talked with team about priorities on user stories for the week.
Date: | 2016-04-13 | Result: | Deliverables for the end of cycle have been discussed and re-evaluated.
Hours Worked: | 1.5 | Problems encountered: | Met with team without Allison
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-04-14 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Met with Austin and then Dr. Dorsey and fellows. Then met back up with Austin.
Date: | 2016-04-15 | Result: | Our group acquired clarifications on requirements from our sponsors. Allison and I met with Austin afterwards. We moved from WAMP to x10hosting for our database and website.
Hours Worked: | 5 | Problems encountered: | WAMP gave us a lot of trouble during the demo with our sponsor.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-04-16 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Group meeting, discusses user stories to work on during the coming week
Date: | 2016-04-17 | Result: | User stories to work on have been assigned
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Fill out status report and timesheet.
Date: | 2016-04-18 | Result: | Status report and timesheet filled out.
Hours Worked: | 0.5 | Problems encountered: | N/A