## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Project Horseshoe Farm | [6 empty] | Completed | 1
| Team Members: | Allison Macdonald, John Carroll, Amanda Bailey, Cesar Sanchez, Mark Ma | [6 empty] | Discarded | 2
| Date: | 2016-04-25 | Cycle: | Cycle 2 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | Horseshoe Farms has requested a webpage which can help streamline their online Remote Tutoring process. Childs should be able to log into a website, see notifications, and navigate to Remote Tutoring materials easily. Notifications will include progress via horseshoes. Based on the day, either reading or math materials will be presented. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Integrate functionality with external components and move to GoDaddy.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Child Log In |  | 1 | 25 | 25 | Completed | 9 | 9
2 | Child View Notifications |  | 1 | 15 | 15 | Completed | 6 | 10
3 | Child Auto Redirect to Lesson |  | 1 | 10 | 5 | Completed | 5 | 5
4 | Child/Remote Tutor start video chat service |  | 1 | 25 | 5 | Completed | 8.25 | 8.25
5 | Child view math worksheets |  | 1 | 10 | 10 | Completed | 3 | 3
6 | Child resume reading from last page |  | 2 | 12 | 0 | Discarded | 0 | 0
7 | Child preview lesson for the day |  | 1 | 10 | 10 | Discarded | 0 | 0
8 | Child/Remote Tutor screen share control |  | 2 | 10 | 0 | Discarded | 2 | 2
9 | Remote Tutor view daily schedule (Child and lesson) |  | 1 | 15 | 0 | Discarded | 3.25 | 3.25
10 | Secured log in |  | 1 | 10 | 10 | Completed | 4 | 4
11 | Admin view Child statistics |  | 2 | 20 | 0 | Discarded | 0 | 0
12 | Admin view Child/Remote Tutor pairing history |  | 2 | 15 | 0 | Discarded | 0 | 0
13 | Team Leader makes recommendations |  | 2 | 25 | 25 | Collaboration | 22.5 | 22.5
14 | Auto login into external websites |  | 2 | 18 | 18 | Collaboration | 8 | 8
15 | Admin pair Child-Remote Tutor |  | 2 | 15 | 15 | Completed | 17 | 17
16 | Remote Tutor Waiting View |  | 2 | 15 | 15 | Completed | 3.75 | 3.75
17 | Log-out/Auto log-out |  | 2 | 5 | 5 | Unstarted | 0 | 0
|  |  | Planned Total | 235 | 138 | Actual Total | 71 | 75

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Project Horseshoe Farm
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Allison Macdonald |  | 4,13,15 | 4,13 | 4,13,15 | 27 | 4 | 4 | 3.25 | 10.25 | 0 | 2 | 15.5 | 25 | 22.75 | 41.25
| John Carroll | 14 |  |  | 4,13,15 | 27 | 0 | 0 | 16 | 26.4 | 0.5 | 1.5 | 2 | 2 | 18.5 | 29.9
| Amanda Bailey | 14 |  |  | 4, 16 | 27 | 0 | 1 | 15.5 | 20.5 | 0 | 1 | 3 | 4.5 | 18.5 | 27
| Cesar Sanchez |  | 4,13 |  |  | 27 | 0 | 0 | 2.5 | 3 | 0 | 2 | 13.25 | 15.75 | 15.75 | 20.75
| Lanxin (Mark) Ma | 4,16 |  |  | 4,16 | 27 | 0 | 4 | 8.5 | 10 | 0 | 2 | 3 | 5.5 | 11.5 | 21.5
[5 empty] | Totals | 135 | [8 empty] | 75.5 | 118.9
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Touch ups on the pairing page (Admin view), Recommendations page is finished (Team Leader), Talky works, We opened kindle on the tutor side for reading day. | [6 empty] | N/A
| Obstacles encountered since last status report: | [6 empty] | Notes:
Time. Improving user interface.
Risks facing the project:
N/A

## Allison's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Allison
Week Ending: |  | 2016-04-25
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-04-19 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Met with team to discuss finishing product.
Date: | 2016-04-20 | Result: | Game plan
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-04-21 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Met with Austin, met with team. Worked on connection functionality.
Date: | 2016-04-22 | Result: | Must find a way around security issues with redirection.
Hours Worked: | 4.5 | Problems encountered: | CORS issues with connection to Talky.io.
Day: | Saturday | Task(s) performed: | Worked on connection functionaltiy.
Date: | 2016-04-23 | Result: | User story for connection finished.
Hours Worked: | 1 | Problems encountered: | x10 can be slow to update to freshly pushed code.
Day: | Sunday | Task(s) performed: | Amend visuals on pairing page and worked on functionality for recommendations. | 22.75
Date: | 2016-04-24 | Result: | No Child option added to pairing page. Front end framework for recommendations complete as well as table.
Hours Worked: | 8.5 | Problems encountered: | Brain doesn't want to keep going.
Day: | Monday | Task(s) performed: | Finished recommendations page and made tweaks on entire product.
Date: | 2016-04-25 | Result: | Ready for demo and delivery. Found a way to force x10 to reinitalize JS.
Hours Worked: | 6.75 | Problems encountered: | x10, logic errors, misunderstanding for passing arrays through AJAX

## Amanda's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Amanda
Week Ending: |  | 2016-04-25
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-04-19 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Meeting- made a plan for the rest of the semester
Date: | 2016-04-20 | Result: | Now have plan for the rest of the semester
Hours Worked: | 1.5 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-04-21 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Meeting with Austin, tried iMacros. Researched adding iMacros as part of a session. Worked on documentation
Date: | 2016-04-22 | Result: | iMacros addon works the way it is advertised.
Hours Worked: | 4 | Problems encountered: | iMacros will be difficult to implement in a functional copacity, because - after downloading and creating the iMacros, it will only be usable for that Child on that computer.
Day: | Saturday | Task(s) performed: | Worked on Test Plan and Procedures for Cycle 3
Date: | 2016-04-23 | Result: | Completed test procedures for remote Child waiting view, remote Child/child connect to talky.io, admin pair remote Child and child, and logout/auto-logout for admin, child, and remote Child
Hours Worked: | 3 | Problems encountered: | The method used for iMacros will not work in a functional copacity, because - after downloading and creating the iMacros - it will only be usable for that Child on that computer. Implementing iMacros via JavaScript will not work because the method iMacros provided uses a function only usable in IE, which talk.io does not support. If iMacros is to be used, further research will need to be conducted.
Day: | Sunday | Task(s) performed: | Team Meeting: Worked on Test Plan and Procedures. Worked on User Documentation. Worked on timesheet. Worked on Design Documentation
Date: | 2016-04-24 | Result: | Completed test procedures for team leader login and logout/auto-logout. In user documentation added the login credentials for x10, the gmail account used for x10, and for the godaddy account.
Hours Worked: | 5 | Problems encountered:
Day: | Monday | Task(s) performed: | Worked on Design Documentation, presentation, and status report.
Date: | 2016-04-25 | Result: | Cycle Report complete, presentaion, and status report.
Hours Worked: | 5 | Problems encountered:

## Cesar's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Cesar Sanchez
Week Ending: |  | 2016-04-25
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-04-19 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Met with team to discuss end goals
Date: | 2016-04-20 | Result: | Plan made for end of project
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-04-21 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Met with Austin. Had to leave after this meeting for a time, but returned later
Date: | 2016-04-22 | Result: | Discussed status with Austin. Worked on user stories with Allison
Hours Worked: | 2.5 | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-04-23 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Met with team to work on visuals and recommendations
Date: | 2016-04-24 | Result: | Made progress on these things
Hours Worked: | 5.5 | Problems encountered: | Tired
Day: | Monday | Task(s) performed: | Met with team to finish product and get presentation together
Date: | 2016-04-25 | Result: | Product is ready for demo, presentation is together
Hours Worked: | 5.75 | Problems encountered: | Still tired

## Mark's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | Lanxin (Mark) Ma
Week Ending: |  | 2016-04-25
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-04-19 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Met with group to talk about plans for the final product. Discussed user story priorities.
Date: | 2016-04-20 | Result: | Plans for final product set.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-04-21 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Met with Mr. Hancock and sponsors to discuss plans for final product. Met with group late in the afternoon to further discuss plans for finished product. Worked on the Child/Remote Tutor start video chat service user story.
Date: | 2016-04-22 | Result: | Group acquired requirement clarifications from the sponsors. Modified user story for Child/Remote Tutor start video chat service.
Hours Worked: | 4 | Problems encountered: | Unable to test user story for Child/Remote Tutor start video chat service on my pc.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2016-04-23 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Worked on user stories and lessons learned sections on cycle report. Discussed user stories that need to be worked on next week. Filled in status report.
Date: | 2016-04-24 | Result: | User stories and lessons learned part on cycle report updated. User stories assigned. Status report filled out.
Hours Worked: | 3 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Met with team to get presentation together and finalize product. Filled in peer evaluation report.
Date: | 2016-04-25 | Result: | Cycle report, presentation, and demo ready. Peer evaluation filled out.
Hours Worked: | 2.5 | Problems encountered: | N/A

## John's Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Horseshoe Farm
Member: |  | John Carroll
Week Ending: |  | 2016-04-25
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2016-04-19 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Meeting
Date: | 2016-04-20 | Result: | N/A
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Thursday | Task(s) performed: | N/A
Date: | 2016-04-21 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Austin, Dr. Dorsey,
Date: | 2016-04-22 | Result: | N/A
Hours Worked: | 2.5 | Problems encountered: | N/A
Day: | Saturday | Task(s) performed: | Worked on iMacros,
Date: | 2016-04-23 | Result: | N/A
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | Group meeting, finishing up development, process
Date: | 2016-04-24 | Result: | Tired
Hours Worked: | 7 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Finalization
Date: | 2016-04-25 | Result: | More tired
Hours Worked: | 5 | Problems encountered: | N/A